## Slide 1: ITEC 2000 Series Policy Updates Kansas IT Project Monitoring and Reporting November 13, 2020
Notes: Several requests were made at the ITAB meeting for volunteers.
View points from different stake holder groups

## Slide 2: Goals
Evaluate IT Projects based on overall business risk as directed by ITEC
Flexibility of oversight process
Identify and close reporting gaps
Simplification of Process
Clearly define ‘IT project’
Process Improvement
Notes: 1. Evaluate based on overall business risk as directed by ITEC - The team is recommending a methodology to evaluate projects based on overall risk rather than solely a dollar threshold.
2. Flexibility of oversight process - The team is recommending language revisions that will allow project management oversight enough latitude to utilize emerging technologies/tools to oversee the evaluation of IT projects.
Identify and close reporting gaps.
  -Currently there is no insight into projects under $250K
  -Planning efforts are not reported if the project is under $250K
  -Currently we do not have an accurate accounting of internal staff costs associated with the project or staff costs once the project is implemented.
  -Currently we do not have an accurate accounting of the total cost of the project ownership.
  -Currently we do not have insight to the total cost of IT project efforts enterprise wide
Simplification of Process - The team is recommending a methodology that allows for different levels of reporting based on risk evaluation. It is the team’s goal to streamline the process, so the reporting level is appropriate to the level of effort and risk.
Clearly define “IT Project” – the current definition has not been updated in more than 10 years.
Process improvement – The team is recommending an automated reporting process to replace the current, more manual process.

## Slide 3: IT Project
Current definition of a reportable IT project:
”means a project for a major computer, telecommunications or other information technology improvement with an estimated cumulative cost of $250,000 or more and has proposed expenditures for: (1) new or replacement equipment or software; (2) upgrade improvements to existing equipment and any computer systems, programs or software upgrades therefore; or (3) data or consulting or other professional services for such a project.”
Notes: All IT projects with a cost of more than $250,000 must follow the process flow for project reporting and monitoring.

## Slide 4: IT Project
Proposed definition:
"Information technology project" means an effort of defined and limited duration which implements, effects a change in or presents a risk to processes, services, security, systems, records, data, human resources or architecture related to technology or information.
Notes: IT project definition doesn’t define what is reportable. Reportability is dependent on business risk.

## Slide 5: What makes a reportable IT Project?
Will the proposed technology effort implement new, effect a change in or present a risk to: | Yes | No
any of your organization’s processes? | ☐ | ☐
any of your organization’s services? | ☐ | ☐
the security systems within your organization? | ☐ | ☐
any other systems within your organization? | ☐ | ☐
the records or data that your organization generates, stores and retrieves? | ☐ | ☐
your organizations human resources? | ☐ | ☐
the information technology architecture for your organizations and/or the enterprise? | ☐ | ☐
If you answered ‘Yes’ to any of the questions/sub-questions then the technology effort IS an information technology project and you will need to complete the IT Risk Determination (IRD) to identify the level of business risk (Nominal, Low, Moderate or High) for this IT Project.
Notes: IT project definition doesn’t define what is reportable. Reportability is dependent on business risk.

## Slide 6
Notes: Reporting Determination

## Slide 7: Risk
Business Risk:
The overall level of risk determined by a business risk assessment which is an analysis of the probability of loss inherent in a project.
Business Risk is not Project Risk:
The risk of project failure does not exclusively dictate the impact of probable loss to the business.

## Slide 8: Business Risk Assessment
Risk | Nominal | Low | Moderate | High
The breadth of business units impacted by the initiative includes: | Only one (1) *BU within a division/agency is impacted. | More than one BU is impacted, but all are within the same program/division. | Multiple BUs across multiple programs/ divisions are impacted | The entire agency or multiple agencies are impacted.
Estimated initiative duration is: | 3 months or less | 3 to 12 months | 12 to 24 months | Greater than 24 months
Estimated initiative cost is: | Less than $250,000 | $250,000 to $1 million | $1M to $10 million | >$10 million
Impact to information security: | Project involves info that is publicly available, and the info system or project is not deemed by the org as mission critical | Project does not directly affect restricted use information but may interact with systems that do. | Project involves restricted use information OR is system deemed a critical system by the organization | Project involves restricted use information AND is system deemed a critical system by the organization
Impact to Core Business Mission | Unsuccessful implementation of the initiative cannot result in the inability to deliver one or more of the organizations core services. | Unsuccessful implementation of the initiative will result in limited ability to deliver one or more of the organizations core services but will not be recognized by external customers. | Unsuccessful implementation of the initiative will result in limited ability to deliver one or more of the organizations core services and will be recognized by external customers. | Unsuccessful implementation of the initiative will result in failure to deliver one or more of the organizations core services.
Familiarity supportability, and maturity of the project technology. | Proven in agency | Proven in public sector organizations with similar lines of business | Proven in public sector | New to the public sector
Notes: Research from other states
Gartner documentation
Drive specific requirements: If Security risk is determined to be high you will need to provide a report to the CISO regardless of overall project risk.
HIGH:
Breadth – Communication Plan approved by CITO
Security – Security Risk Assessment approved by CISO
Business Mission – Mitigation Plan approved by agency head
Architecture – Architecture statement approved by ITEC
Duration – Kansas Certified PM
Cost – IV&V

## Slide 9: Business Risk Levels
Nominal
  No on-going reporting
  Requires no Branch CITO approval
Low
  Simplified plan reporting
  Minimal quarterly reporting
  Requires no Branch CITO approval
Moderate
  On-going reporting
  Requires Branch CITO approval
High
  On-going reporting
  Requires Branch CITO approval
  Requires IV&V

## Slide 10: Current Activities
ITEC Policy Review Team is in process of finalizing deliverables and process flow
  Project Manager Advisory Team participating in process/document review

## Slide 11: Next Steps
Presentation of draft policies and statutes to ITEC at next meeting on 12/15/20.
Proposed statute changes submitted at 2021 legislative session
Automation of determination & reporting processes
  Currently evaluating products that will allow online filing/submission of project documents
Training
  The KITO office will be rolling out training to all state agencies in the spring.

## Slide 12: Questions?